## WIP
| Contracts in Progress & Closed Job Schedule |  |  |  |  | Contractor
Date
A | B | C | D | E | F | G | H | I | J | K | L | M | N
Contractor Job No. | Job Description | Revised Contract Price | Est. Total Cost | Cost Incurred to Date | Total Amount Billed to Date | Estimated Completion Date | Est. Gross Profit (Col C - Col D) | Percentage Complete (Col E / Col D) | Estimated Cost to Complete (Col D - Col E) | Earned Profit (Col I x Col H) | Earned Revenue (Col K + Col E) | Overbilling/ (Underbilling) Col F- Col L | Est Gross Profit Percentage
|  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Totals |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!